## Slide 1: «Competencies for living and working in the 21st century: A capacity development toolkit for curriculum innovations in African Countries» International Workshop – Nairobi (Kenya), 22-26 June 2009
Follow-up of the Geneva seminar

## Slide 2
Activities | Status
- Workshop Report | Report delayed – will be sent out as a package, including Kigali, Grenva and Nairobi
-Conclusions of the Geneva seminar | Prepared
- Refining the Toolkit structure and content outline | Feedback from country teams First comprensive draft Review meeting in Geneva (June 09) Secod revised comprehensive draft
Planned national workshop | Postponed for after Nairobi
Organization of Kenya workshop | Agreement with, and support of MOE, Kenya Agenda Conceptual note Instructions to country teams Logistic preparations

## Slide 3
Next steps | Status
-Preparing an advanced version of the Toolkit - Preparing for the pilot testing | Comprehsnsive draft by early August 09 Pilot testing strategy agreed upon
- One day national workshop for dissemination and sharing of the project process and adcvanced version of the Toolkit | Late August/Sept. 09
Field testing of the Toolkit in selected countries | Feedback to be prepared by end of Sept. 09
- Final project seminar in Frankfurt and finalisation of the Toolkit | 12-16 Oct. 09 – Frankfurt seminar Finalised Toolkit integrating the feedback from countries Discussing the usage of the Toolkit and other resources Suggestions for follow-up
Publication of the Toolkt | November, IBE / GTZ

## Slide 4: Other issues
Completion and publication of the new version of the Study on preparation for life and work
Preparing a new project proposal for 2010-2013
Fund raising