## Slide 1: «Competencies for living and working in the 21st century: A capacity development toolkit for curriculum innovations in African Countries» International Workshop – Nairobi (Kenya), 22-26 June 2009
Follow up activities Nairobi workshop

## Slide 2
Activity | Timing
Reports on workshops from Kigali, Geneva and Nairobi | Mid-July 09
Letter of information to the Ministers of Education on status of activities | 03rd July 09
Completion of toolkit for piloting - Final writing by expert group / selected country represent. - Meeting of core editorial team in Geneva | July to mid August 09 04th/05th August 09
Dissemination of toolkit in all aprticipating countries -Development of guidelines for pilot testing by GTZ -Planning and budgeting for workshops by country teams -Planning to be sent to IBE and GTZ -Agreement on activities with IBE and GTZ -1 day workshop in the countries -Report on country workshops to IBE/GTZ | Mid-July 09 July 09 25th July 09 1st August 09 August/September 09 30th September 09

## Slide 3
Next steps | Status
Piloting in three selected countries (incl. dissemination) -Development of guidelines for pilot testing by GTZ Planning and budgeting for possible activities country teams -Planning to be sent to IBE and GTZ -Agreement on activities with IBE and GTZ -Country teams start preparation of activities -Start of agreed piloting activities - Report of results pilot testing | Mid-July 09 July 09 25th July 09 1st August 09 From 1st August 09 appr. mid Ausgust 30th September 09
Completion of toolkit by editorial group -Gathering feedback testing and dissemination -Preparation of final toolkit | Septemb./October 09
Final Frankfurt workshop -Conceptual planning / preparation of Frankfurt workshop - Workshop to finalize toolkit and plan possible next steps | Septemb./October 09
Designing and publication of the toolkit by IBE/GTZ | Novemb./Decemb. 09
Preparation of a new project proposal and funds mobilaization by IBE, GTZ and Country Teams | Novemb./Decemb. 09

## Slide 4
Other measures:
  Completion, designing and publication of the study on relevance of curricula for life and work