## Slide 1: «Competencies for living and working in the 21st century: A capacity development toolkit for curriculum innovations in African Countries» International Workshop – Nairobi (Kenya), 22-26 June 2009
Pilot testing of the Toolkit;
Identification/selection of the pilot countries

## Slide 2: Why piloting the toolkit?
National dissemination workshops to raise awareness and get feedback from stakeholders, all countries
More in depth pilot testing, three countries

## Slide 3: Why pilot testing the toolkit?
To provide preliminary feedback on how the toolkit works in practice
How the toolkit can meets the needs for curriculum innovations at national level
Get recommendations and suggestions for improving the toolkit in view of its finalization
Focus: Content and implementation

## Slide 4: National dissemination workshops (detailed guidelines will be issued by IBE and GTZ)
Who?
  All participating countries
Why?
  National dissemination to raise awareness
  Get feedback from stakeholders
What?
  Information on toolkit to stakeholders
  Discuss vadility for national curriculum innovations
  Feedback / report to editorial team

## Slide 5: Calendar dissemination toolkit
Planning and budgeting for workshops by country teams, July 09
Planning sent to IBE and GTZ, 25th July 09
Agreement on activities with IBE and GTZ, 1st August 09
1 day workshop in the countries, August/September 09
Feedback / report on country workshops to IBE/GTZ, latest 30th September 09

## Slide 6: Possible activities for in depth pilot testing (detailed guideleines will be issued by IBE and GTZ)
Expert focus groups for feed back
Consultations with stakeholders (e.g. meetings, questionnaires)
Capacity development activities targeting decision makers, curriculum development departments and teacher training institutions
Testing selected parts of the toolkit in real processes of curriculum development
Mix of different options is possible;
also new suggestions …
be aware of time and budget limitations

## Slide 7: Calendar of pilot testing
Information letter on follow up and pilot testing by 03rd July
Development of guidelines for pilot testing, mid-July
Planning and budgeting of possible activities by country teams, July 2009
Planning to be sent to IBE and GTZ not later than 25th July 2009
Agreement on activities with IBE and GTZ by 1st August 2009
Country teams start preparation of activities by 1st August 2009
Start of activities once the revised toolkit has been received, appr. mid August
Report of results pilot testing latest 30th September 2009

## Slide 8: Criteria to identify and select countries for piloting
Three languages should be represented
3 regions should be represented
6 weeks time for testing and reporting
Availability and committment of country teams mid August to end September 2009
Availability of country teams12th to 16th October 2009 (Frankfurt workshop)
Presence, commitment and availability of UNESCO country offices
Commitment of Ministry